## Jira
Issue key | Issue id | Project name | Parent summary | Summary | Issue Type | Description | Attachment | Attachment | Priority | Status | Project key | Project type | Project lead | Created | Parent key
SCRUM-19 | 10059 | Demo-Shopping | Card | Console error: Cannot read properties of null (reading 'addEventListener') | Bug | *Steps to reproduce:* # Open the page # Open Chrome DevTools # Go to Console tab *Actual result:* {quote}Console shows an uncaught TypeError: Cannot read properties of null (reading 'addEventListener') in app.js.{quote} *Expected result:* {quote}No JavaScript errors in the browser console.{quote} *Environment:* * Browser: Chrome * Page: [https://intern.demoshopping.ru/about¦https://intern.demoshopping.ru/about¦smart-link] | 15/Dec/25 2:44 PM;44f062a5-6cf2-4a64-ab06-5914b05f41ab;Screenshot 2025-12-15 at 2.38.28 pm.png;https://shlyah29.atlassian.net/rest/api/3/attachment/content/10049. | 15/Dec/25 2:44 PM;44f062a5-6cf2-4a64-ab06-5914b05f41ab;Screenshot 2025-12-15 at 2.39.09 pm.png;https://shlyah29.atlassian.net/rest/api/3/attachment/content/10048 | Medium | To Do | SCRUM | software | Александра Шляхтова | 15/Dec/25 2:42 PM | SCRUM-14
SCRUM-18 | 10057 | Demo-Shopping | Card | Text alignment issues on Cart and Payment pages | Bug | {quote}The same text alignment issue is observed on multiple pages: – Cart page – Payment page Page headers and text are visually misaligned compared to the design.{quote} | 15/Dec/25 10:24 AM;44f062a5-6cf2-4a64-ab06-5914b05f41ab;Screenshot 2025-12-15 at 10.20.59 am.png;https://shlyah29.atlassian.net/rest/api/3/attachment/content/10046 | 15/Dec/25 2:26 PM;44f062a5-6cf2-4a64-ab06-5914b05f41ab;Screenshot 2025-12-15 at 2.19.37 pm.png;https://shlyah29.atlassian.net/rest/api/3/attachment/content/10047 | Low | To Do | SCRUM | software | Александра Шляхтова | 15/Dec/25 10:24 AM | SCRUM-14
SCRUM-17 | 10055 | Demo-Shopping | Card | Typo in header menu: "Ктолог" instead of "Каталог" | Bug | h3. Steps to Reproduce # Open [https://intern.demoshopping.ru/cart¦https://intern.demoshopping.ru/cart¦smart-link] # View the header navigation menu ---- h3. Actual Result * Menu item is displayed as *"Ктолог"* ---- h3. Expected Result * Menu item should be displayed as *"Каталог"* ---- h3. Environment * Browser: Chrome * OS: macOS | 15/Dec/25 10:08 AM;44f062a5-6cf2-4a64-ab06-5914b05f41ab;Screenshot 2025-12-15 at 9.58.06 am.png;https://shlyah29.atlassian.net/rest/api/3/attachment/content/10044 |  | Medium | To Do | SCRUM | software | Александра Шляхтова | 15/Dec/25 10:11 AM | SCRUM-14
SCRUM-16 | 10053 | Demo-Shopping | Card | Cart items disappear when navigating back from checkout and reappear during checkout | Bug | h3. Steps to Reproduce # Add a product to the cart # Go to *Checkout* # Do not complete the order # Navigate back to the *Home page* # Open the *Cart* — cart is empty # Add another product to the cart # Go to *Checkout* again ---- h3. Actual Result * Previously added product disappears from the cart * Only the newly added product is shown * During checkout, the previously disappeared product appears again in the cart ---- h3. Expected Result * Cart content is consistent across all pages * Products added to the cart do not disappear * Cart data remains the same when navigating back from checkout ---- h3. Environment * Browser: Chrome * OS: macOS | 15/Dec/25 9:19 AM;44f062a5-6cf2-4a64-ab06-5914b05f41ab;Screen Recording 2025-12-15 at 9.12.26 am.mov;https://shlyah29.atlassian.net/rest/api/3/attachment/content/10041 | 15/Dec/25 9:56 AM;44f062a5-6cf2-4a64-ab06-5914b05f41ab;Screenshot 2025-12-15 at 9.55.20 am.png;https://shlyah29.atlassian.net/rest/api/3/attachment/content/10042 | Highest | To Do | SCRUM | software | Александра Шляхтова | 15/Dec/25 9:23 AM | SCRUM-14
SCRUM-14 | 10050 | Demo-Shopping |  | Card | Epic |  |  |  | Medium | To Do | SCRUM | software | Александра Шляхтова | 15/Dec/25 8:01 AM
SCRUM-13 | 10049 | Demo-Shopping | Card | Cart is not loaded: GET /getCart returns 404 | Bug | h3. Steps to Reproduce # Log in to the application # Open *Cart* page # Open *DevTools → Network* # Refresh the page ---- h3. Actual Result * *GET /getCart* request returns *404 Not Found* * Cart data is not loaded ---- h3. Expected Result * *GET /getCart* returns *200 OK* * Cart data is displayed correctly ---- h2. Environment * Browser: Chrome 143 * OS: macOS * URL: [https://intern.demoshopping.ru/cart¦https://intern.demoshopping.ru/cart¦smart-link] | 15/Dec/25 7:57 AM;44f062a5-6cf2-4a64-ab06-5914b05f41ab;Screenshot 2025-12-15 at 7.44.07 am.png;https://shlyah29.atlassian.net/rest/api/3/attachment/content/10037 |  | Highest | To Do | SCRUM | software | Александра Шляхтова | 15/Dec/25 7:58 AM | SCRUM-14