## Jira (5)
Issue key | Issue id | Parent summary | Summary | Issue Type | Description | Attachment | Priority | Status | Sprint | Project type | Project lead
SCRUM-26 | 10110 | Shopping list | App crashes when DELETE button is pressed multiple times rapidly | Bug | The application crashes when the DELETE button is pressed multiple times in rapid succession. This is a critical bug that causes app termination and poor user experience. Steps to Reproduce: # Launch the Shopping List app # Add a task "Молоко" # Rapidly tap the "DELETE" button multiple times (5-10 times quickly) # Observe app behavior Expected Result: * Task should be deleted once * DELETE button should be disabled or hidden after first tap * App should remain stable * No crash should occur Actual Result: * App crashes/closes unexpectedly * Task is deleted but app terminates * User is forced to restart the app Technical Notes: This appears to be a race condition or lack of button state management. The DELETE button should be disabled immediately after first tap to prevent multiple rapid clicks. Impact: * High user impact * Data loss risk (unsaved tasks) * Poor user experience * App instability Device: Android Emulator (Medium Phone API 36.1) OS: Android API 36 | 03/Jan/26 2:39 PM;44f062a5-6cf2-4a64-ab06-5914b05f41ab;FATAL EXCEPTION_ main.txt;https://shlyah29.atlassian.net/rest/api/3/attachment/content/10093 | Highest | To Do | Shopping list | software | Александра Шляхтова
SCRUM-25 | 10108 | Shopping list | Task can be saved with only spaces - empty task validation bypassed | Bug | The application allows saving a task that contains only spaces, which bypasses the "empty task" validation. This creates meaningless tasks in the list. Steps to Reproduce: # Launch the Shopping List app # Tap on the text input field # Enter only spaces " " (5-10 spaces, no other characters) # Tap "ДОБАВИТЬ ЗАДАЧУ" button Expected Result: * Toast message "Задача не может быть пустой" should appear * Task should NOT be added * Empty space-only input should be treated as empty task Actual Result: * Task is added to the list * Task appears as blank/empty item in the list * No validation error appears * Space-only task is treated as valid input Notes: This bypasses the empty task validation. The app should trim spaces before validation or treat space-only input as empty. Device: Android Emulator (Medium Phone API 36.1) OS: Android API 36 |  | Medium | To Do | Shopping list | software | Александра Шляхтова
SCRUM-24 | 10106 | Shopping list | Task can be saved with leading and trailing spaces | Bug | The application allows saving tasks with leading and trailing spaces, which leads to poor data quality and inconsistent task names display. Steps to Reproduce: # Launch the Shopping List app # Tap on the text input field # Enter " Молоко " (with spaces before and after) # Tap "ДОБАВИТЬ ЗАДАЧУ" button Expected Result: * Spaces should be automatically trimmed * Task should be saved as "Молоко" (without leading/trailing spaces) OR * Validation error should appear if spaces are not allowed Actual Result: * Task is saved as " Молоко " with all spaces * Leading and trailing spaces are preserved * Task appears with extra spacing in the list Notes: This is a common UX issue. Best practice is to trim whitespace from user input to maintain data consistency. | 03/Jan/26 2:31 PM;44f062a5-6cf2-4a64-ab06-5914b05f41ab;Screenshot_20260103_143049.png;https://shlyah29.atlassian.net/rest/api/3/attachment/content/10089 | Medium | To Do | Shopping list | software | Александра Шляхтова
SCRUM-23 | 10104 | Shopping list | Edit function allows entering special characters - validation rule bypassed | Bug | When editing an existing task via long tap, the application allows entering special characters, which violates the validation rule "only Russian letters allowed". This bypasses the validation that works correctly when adding a new task. Steps to Reproduce: # Launch the Shopping List app # Add a valid task "Молоко" (Russian letters only) # Long tap on task "Молоко" # Edit dialog appears # Clear the field and enter "@#$%" (special characters) # Tap "СОХРАНИТЬ" button Expected Result: * Toast message "Задача должна быть на русском языке" should appear * Task should NOT be updated with special characters * Task "Молоко" should remain unchanged Actual Result: * Task is updated to "@#$%" * No validation error appears * Special characters are accepted in edit mode Notes: This is inconsistent behavior - the same validation that works for "Add" function doesn't work for "Edit" function. Similar to BUG-2 (numbers validation bypass). | 03/Jan/26 2:29 PM;44f062a5-6cf2-4a64-ab06-5914b05f41ab;Screenshot_20260103_142855.png;https://shlyah29.atlassian.net/rest/api/3/attachment/content/10087 | High | To Do | Shopping list | software | Александра Шляхтова
SCRUM-22 | 10102 | Shopping list | Edit function allows entering numbers - validation rule bypassed | Bug | When editing an existing task via long tap, the application allows entering numbers, which violates the validation rule "only Russian letters allowed". This bypasses the validation that works correctly when adding a new task. Steps to Reproduce: # Launch the Shopping List app # Add a valid task "Молоко" (Russian letters only) # Long tap on task "Молоко" # Edit dialog appears # Clear the field and enter "123" (numbers) # Tap "СОХРАНИТЬ" button Expected Result: * Toast message "Задача должна быть на русском языке" should appear * Task should NOT be updated with numbers * Task "Молоко" should remain unchanged Actual Result: * Task is updated to "123" * No validation error appears * Numbers are accepted in edit mode Notes: This is inconsistent behavior - the same validation that works for "Add" function doesn't work for "Edit" function. | 03/Jan/26 2:27 PM;44f062a5-6cf2-4a64-ab06-5914b05f41ab;Screenshot_20260103_142647.png;https://shlyah29.atlassian.net/rest/api/3/attachment/content/10085 | Highest | To Do | Shopping list | software | Александра Шляхтова
SCRUM-21 | 10100 | Shopping list | Incorrect character limit - accepts 24 characters instead of 25 | Bug | The application accepts only 24 characters for task name, but according to requirements the limit should be 25 characters. Steps to Reproduce: # Launch the Shopping List app # Tap on the text input field # Enter exactly 24 Russian characters (e.g., "Молоко и хлеб на ужин се") # Tap "ДОБАВИТЬ ЗАДАЧУ" button # Task is added successfully # Now try to enter 25 characters (e.g., "Молоко и хлеб на ужин сег") # Tap "ДОБАВИТЬ ЗАДАЧУ" button Expected Result: Task with 25 characters should be added successfully. Toast message should appear only when entering MORE than 25 characters (26+). Actual Result: Toast message "Задача не должна превышать 25 символов" appears at 25 characters. Task is not added. Only 24 characters are accepted. | 03/Jan/26 2:23 PM;44f062a5-6cf2-4a64-ab06-5914b05f41ab;Screenshot_20260103_142231.png;https://shlyah29.atlassian.net/rest/api/3/attachment/content/10083 | Medium | To Do | Shopping list | software | Александра Шляхтова